Progress Report February 17, 2025

Project Title: An ecological and oceanographic baseline to inform offshore wind development over the continental shelf off the coast of New Jersey

Authors: Grace Saba & Josh Kohut

Project Overview:

New Jersey has set a goal to procure half of its energy from renewable resources by 2030. With offshore wind construction scheduled to begin in the next couple years, it is critical that oceanographic and ecological baseline monitoring begin immediately. In this 2-year project, a glider-based program will simultaneously map oceanographic and ecological parameters that will inform each of the New Jersey Offshore Wind Research and Monitoring Initiative’s (RMI) research priorities. The project consists of glider deployments (11 per year), data management, and data analysis and product development relevant to RMI research priorities.

A seasonal baseline survey is being conducted with a pair of gliders deployed in each season over two years with a full complement of available sensors to simultaneously map oceanographic and ecological variables. The zig-zag glider missions cover an area from Sandy Hook down to Atlantic City, from near shore extending out across the shelf. This ensures that the monitoring occurs both on established long-term transects for historical context and within offshore wind lease areas. To accommodate the larger sensor suite and mitigate interference between active and passive sensors this approach utilizes two gliders paired for each seasonal mission. One glider is equipped with a CTD to determine water depth, temperature, salinity, and density; an optics puck measuring chlorophyll-a, backscatter, and colored dissolved organic matter (CDOM) fluorescence; an optode measuring dissolved oxygen; and a DMON passive acoustics sensor for marine mammal monitoring and detection. The second glider is equipped with an optics puck and an Acoustic Zooplankton Fish Profiler (AZFP) multi-frequency echo sounder for active acoustic detection of pelagic organisms. Similar to the first glider, the second glider has a CTD, but this CTD package also includes an integrated pH sensor for ocean acidification applications. Both gliders carry a fish telemetry receiver to track tagged species moving through the region. In addition to these paired seasonal missions, we will deploy a third glider equipped with the CTD/pH, optics puck, optode, and VEMCO receiver 3 times each year. These deployments fill coverage gaps in the seasonal glider deployments from the onset of seasonal stratification associated with the Cold Pool formation in the spring to the physical breakdown in the fall.

The data quality assurance/quality control (QA/QC) and management for this project is based on the considerable infrastructure already in place at Rutgers. The project data management includes the preservation, documentation, and sharing of data collections, and other related research and education products. The project will generate new data (near real-time and delayed mode QC’d datasets), and the specific data sets managed by this project include physical, chemical, and biological variables sampled by both glider and vessel platforms.

The baseline data provided by the glider monitoring program will be used as input to a series of analyses and products developed by our faculty and students. The specific products and analysis completed will be determined following consultation with the RMI leadership team.

Work Progress During This Reporting Period (October 2024 – January 2025):

Equipment updates: In the April 2024 progress report, we described the issue regarding the failure of the 200 kHz channel on the fish-configured AZFP echosounder housed on glider ru39 (noticed after the summer 2023 paired mission). Since then, (ASL) diagnosed and repaired the issue. This repaired AZFP sensor was used during the Fall 2024 paired mission. No reoccurrence of the failure of the 200 kHz channel was observed; however, when the AZFP sensor calibrations were conducted in January 2025, the dB offsets for the 120 kHz channel were high (nearly a 20 dB difference between expected and observed target strength of the calibration sphere). Therefore, we are sending the zooplankton-configured AZFP back to ASL for testing and potential repair and the fish-configured AZFP will be used in the upcoming winter (February) glider mission.

Glider deployments: We have conducted a total of 18 glider deployments for this project, 3 in the current reporting period. We conducted a paired Spring 2023 mission (4/20 - 5/12; previous reporting period – June 2023 report), two single-glider gap fill missions (06/29 - 08/02 and 09/20 - 10/19; previous reporting period – November 2023 report), a paired glider Summer 2023 mission (08/17 - 09/20; previous reporting period – November 2023 report), a paired glider Fall 2023 mission (11/03 – 12/05; previous reporting period – November 2023 report), a paired glider Winter 2024 mission (02/15 - 03/14; previous reporting period – April 2024 report), a paired glider Spring 2024 mission (04/29 – 05/29; previous reporting period, September 2024 report), a single-glider gap fill mission (06/12 – 07/09; previous reporting period, September 2024 report), a paired glider Summer 2024 mission (07/23 – 08/23; previous reporting period, September 2024 report), a single-glider gap fill mission (09/04 – 10/05; this report), and a paired glider Fall 2024 mission (10/21 – 11/19; this report). These 18 deployments nearly conclude two full annual cycles of data collection, the last of which will be the paired glider winter mission later this month. The approximate path taken for each glider mission is indicated in the figure (right), and sensors aboard each glider and mission are included in the table below. Details of the data collected over the Early Fall Gap-Fill and Fall 2024 missions are described in greater detail below in ‘Preliminary Results’.

Additionally, we have recently begun pairing the RMI-funded deployments with the other nearshore glider deployments funded by NJDEP’s Bureau of Marine Water Monitoring. We have also added a pH sensor (purchased previously using funds from non-NJDEP or RMI projects) to some deployments of the nearshore glider (at no cost to this project) to not only expand the spatial coverage of the carbonate chemistry monitoring, but also to address and monitor for potential multi-stressor conditions (low pH/Ω and dissolved oxygen) that were observed during the summer 2023 missions.

| Deployment time | Glider name | Parameters measured |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Salinity, Temperature, Deptha | pHb | Chlorophyll, backscatter, CDOMc | Dissolved oxygend | Zooplankton biomass (active acoustics)e | Fish biomass (active acoustics)f | Marine mammal detectiong | Tagged fish detectionh |
| Spring 2023 | ru39 | X | X | X |  | X |  |  | X |
| Spring 2023 | ru41* | X |  | X | X |  |  | X | X |
| Gap fill: July 2023 | ru40 | X |  | X | X |  |  | X | X |
| Summer 2023 | ru39 | X | X | X |  |  | X |  | X |
| Summer 2023 | ru40 | X |  | X | X |  |  | X | X |
| Gap fill: Sept 2023 | ru34 | X | X | X | X |  |  |  | X |
| Fall 2023 | ru39 | X | X | X |  | X |  |  | X |
| Fall 2023 | ru40 | X |  | X | X |  |  | X | X |
| Winter 2024 | ru39 | X | X | X |  | X |  |  | X |
| Winter 2024 | ru40 | X |  | X | X |  |  | X | X |
| Spring 2024 | ru39 | X | X | X |  | X |  |  | X |
| Spring 2024 | ru40 | X |  | X | X |  |  | X | X |
| Gap fill: June 2024 | ru43 | X | X | X | X |  |  |  | X |
| Summer 2024 | ru39 | X | X | X |  |  | X |  | X |
| Summer 2024 | ru40 | X |  | X | X |  |  | X | X |
| Gap fill: Aug 2024 | ru43‡ | X | X | X | X |  |  |  | X |
| Gap fill: Sept 2024 | ru43 | X | X | X |  | X |  |  | X |
| Fall 2024 | ru39 | X | X | X |  |  | X |  | X |
| Fall 2024 | ru40 | X |  | X | X |  |  | X | X |
| Winter 2025 | ru39 | X | X | X |  | X |  |  | X |
| Winter 2025 | ru40 | X |  | X | X |  |  | X | X |

aSensor = Deployment completed

aSensor = Deployment ongoing

aSensor = Deployment missed

aSensor = Sea-Bird CTD

bSensor = deep-sea ISFET based pH sensor, coupled with aCTD

cSensor = Wetlabs FLBBCD-SLC ECOpuck

dSensor = Aanderaa optode

eSensor = ASL Acoustic Zooplankton Fish Profiler (AZFP), a multi-frequency echosounder configured for zooplankton (120, 200, 455, 769 kHz)

fSensor = ASL Acoustic Zooplankton Fish Profiler (AZFP), a multi-frequency echosounder configured for pelagic fishes (38, 120, 200 kHz)

gSensor = WHOI DMON

hSensor = Vemco Rx-Live or Vemco VMT

*glider lost; replacement ordered

‡ru43 = new glider (replacement to lost glider ru41)

General note on above table: While the deployment schedule and sensors that will be targeted for use during those deployments are more concrete, glider names and their respective deployment assignments listed above are tentative and will be based on which gliders are available based on glider and sensor bay maintenance schedules.

Developments in real-time data visibility: As part of our ongoing effort to ensure real-time data availability, we added calculations of Total Alkalinity and Aragonite Saturation State for the New Jersey/New York Bight region to our glider data processing pipeline. These data products are available in our real-time datasets that are distributed on RUCOOL's glider ERDDAP server. The code for these improvements is publicly available in our rugliderqc Github repository. In order to complete this, we updated our Total Alkalinity (TA)-salinity regression analysis to incorporate more vessel-based data in the New Jersey/New York Bight region. The previous analysis included discrete samples collected during the summer 2015 East Coast Ocean Acidification (ECOA) cruise. This dataset was paired with water sampling done during seasonal glider deployments and recoveries, and the linear relationship between TA and salinity was calculated for each season. Any seasonal differences in the TA-salinity relationship were based solely on the glider-based water sampling due to a lack of vessel-based data.

To incorporate more vessel-based data into the analysis, we used the 2021 CODAP-NA dataset in addition to publicly available cruise data downloaded from the NCEI Ocean Carbon and Acidification Data System (OCADS) data portal. These datasets were filtered to include sampling locations within the New York Bight at depths less than 200m (maximum glider depth), and salinity/TA QC flags were applied (when available).

The resulting vessel-based New York Bight dataset includes Niskin bottle samples as well as surface flow-through and underway samples from 31 oceanographic cruises from 2006-2022. This expansion of the vessel-based dataset now allows for more robust seasonal TA-salinity regressions that are used to estimate TA in glider datasets.

Data product development: The resulting data from the project’s first year of deployments is starting to be utilized for research and the development of data products by data analysts from our Masters in Operational Oceanography program and other graduate students. Our team is currently working on a manuscript that will present a full seasonally-resolved description of zooplankton abundance, biomass, and distribution patterns in New Jersey shelf waters. We are applying generalized linear models to the data to determine if ocean fronts play a role in driving zooplankton aggregations or patches. This manuscript is an expansion of initial efforts conducted by Nicholas Occhiogrosso, a student advised by PI Saba who completed our Masters in Operational Oceanography program last summer. Additionally, PhD student Jacob Kuenzli (advised by PI Saba and collaborating with Drs. Keith Dunton and Jason Adolf) at Monmouth University) is currently conducting research that is utilizing moored- and glider telemetry receiver data (from this project as well as historical projects) to determine historical presence/absence, distribution, and habitat use of tagged elasmobranchs. These research efforts are just beginning.

Data Availability: The data are reported in two ways. Real-time data are those data sent back to shore via the satellite connection during the mission and may not include the full dataset. Delayed mode data are those data recovered from the glider once it is recovered and include the full dataset. The QA/QC associated with both data reporting are described in the project QAPP document. The status of data reporting for each mission is summarized below.

- Spring 2023 paired

  - ru39: delayed mode data are available on ERDDAP

  - ru41 (lost): real-time raw data are available on ERDDAP

- June/July 2023 gap-fill

  - ru40: delayed mode data are available on ERDDAP

- Summer 2023 paired

  - ru39: delayed mode data available on ERDDAP

  - ru40: delayed mode data available on ERDDAP

- September/October 2023 gap-fill

  - ru34: delayed mode data available on ERDDAP

- Fall 2023 paired

  - ru39: delayed mode data available on ERDDAP

  - ru40: delayed mode data (pre-brake failure) and delayed mode data (redeploy after fix of glider brake) available on ERDDAP

- Winter 2024 paired

  - ru39: delayed mode data available on ERDDAP

  - ru40: delayed mode data available on ERDDAP

- Spring 2024 paired

  - ru39: delayed mode data available on ERDDAP

  - ru40: delayed mode data available on ERDDAP

- June 2024 gap-fill

  - ru43: delayed-mode data available on ERDDAP

- Summer 2024 paired

  - ru39: delayed-mode data available on ERDDAP

  - ru40: delayed-mode data available on ERDDAP

- September 2024 gap-fill

  - ru43: delayed-mode data available on ERDDAP

- Fall 2024 paired:

  - ru39: delayed-mode data available on ERDDAP

  - ru40: delayed-mode data available on ERDDAP

Preliminary Results:

Oceanographic data

Seasonal progressions: Starting with the first glider deployments for this project up until the date of this progress report, RMI gliders were in coastal shelf waters 337 out of 670 days (50% coverage) and traveled 9558 km. This reporting period started with the paired Spring 2024 mission, which notably observed anomalously cold bottom water temperatures. The minimum bottom temperature during the Spring 2024 mission was measured at 6.02˚C, and the Cold Pool minimum temperature stayed near or below 7˚C through the gap fill and Summer 2024 missions. Average Cold Pool temperature during this time of year is typically between 8-10˚C. Also, stratification set up was observed during the paired Spring 2024 mission (end of May), and this seems to have occurred at 1 month or more later than the previous year (end of April 2023). Maximum surface temperatures during the Summer 2024 deployment reached 26.1 ˚C. Bottom seawater pH and Ω during Summer 2024 were the lowest we have observed in our history of glider-based ocean acidification monitoring (since 2018). Minimum bottom pH values (7.6) and Ω values (0.64) covered a large proportion of the shelf, particularly in the shallower areas. However, bottom dissolved oxygen remained above 5 mg/L. We attribute the low bottom temperature, pH, and Ω, and relatively high dissolved oxygen, to an unusually high volume flux of Labrador Slope Water onto the MAB shelf this year,.

Complete cross-sections of (from top to bottom) temperature, chlorophyll concentrations, dissolved oxygen concentrations, pH, and derived aragonite saturation state (Omega) measured along the mission tracks during the Early fall gapfill 2024 (left panel) and Fall 2024 (right panel) glider deployments.

Acoustic data

Passive acoustic data: The passive acoustic data and the status of data retrieval and processing are summarized in the table below. Locations for marine mammal detections can be viewed on the links provided in the table below, and these are also openly accessible at http://robots4whales.whoi.edu/.

| Deployment/glider name | Vemco detection data info and/or status | DMON detection data info and status |
| --- | --- | --- |
| Spring 2023 paired |  |  |
| ru39 | No vemco detections | N/A. No DMON sensor. |
| ru41 | No vemco detections | 3 humpback detection days |
| Early summer (June/July) 2023 gap fill |  |  |
| ru40 | 84 detections from 8 unique tags registered in the MATOS database, 25 detections from 2 unique tags not registered in the MATOS database | 2 fin whale detection days |
| Summer 2023 paired |  |  |
| ru39 | 26 detections from 5 unique tags registered in the MATOS database, 8 detections from 1 unique tag not registered in the MATOS database | N/A. No DMON sensor. |
| ru40 | 71 detections from 11 unique tags registered in the MATOS database, 11 detections from 3 unique tags not registered in the MATOS database | 18 fin whale detection days |
| Early fall (September/October) 2023 gap-fill |  |  |
| ru34 | 849 detections from 46 tags (preliminary from Rx-Live), official results and contact points waiting on MATOS data push (in progress) | N/A. DMON swapped for pH to continue monitoring dissolved oxygen and pH |
| Fall 2023 paired |  |  |
| ru39 | 13 detections from 3 unique tags registered in MATOS database, 44 detections from 11 unique tags not registered in MATOS database | N/A. No DMON sensor. |
| ru40 | 56 detections from 12 tags (preliminary from Rx-Live), official results and contact points waiting on MATOS data push (in progress) | 15 total whale detection days including fin whales (11 detection days), humpback whales (2 detection days), and North Atlantic right whales (NARW, 5 detection days). *Note: Due to the detection of NARW presence from this glider, NOAA Fisheries triggered a voluntary Right Whale Slow Zone in the detection area that started on 11/17 and was effective until 12/2. |
| Winter 2024 paired |  |  |
| ru39 | 18 detections from 4 tags not registered in MATOS database | N/A. No DMON sensor. |
| ru40 | 140 detections from 12 tags (preliminary from Rx-Live), official results and contact points waiting for MATOS data push (in progress) | 24 total whale detection days including sei whales (1 detection day), fin whales (19 detection days), and humpback whales (16 detection days). |
| Spring 2024 paired |  |  |
| ru39 | 5 detections from 2 unique tags registered in MATOS database, plus 165 detections from 8 unique tags not registered in the MATOS database. | N/A. No DMON sensor. |
| ru40 | 372 detections from 35 tags (preliminary from Rx-Live), official results and contact points waiting for next MATOS data push (October) | 22 total whale detection days, including sei whales (12 detection days), fin whales (14 detection days), right whales (1 detection day), and humpback whales (22 detection days) |
| Early summer (June/July) 2024 gap-fill |  |  |
| ru43 | 40 detections from 9 unique tags registered in MATOS database, plus 52 detections from 10 unique tags not registered in the MATOS database. | N/A. No DMON sensor. |
| Summer 2024 paired |  |  |
| ru39 | 19 detections from 4 unique tags registered in MATOS database, plus 62 detections from 7 unique tags not registered in the MATOS database. | N/A. No DMON sensor. |
| ru40 | 565 detections from 36 tags (preliminary from Rx-Live), official results and contact points waiting for MATOS data push (in progress) | 19 total whale detection days, including sei whales (1 detection day), fin whales (19 detection days), right whales (2 detection days), and humpback whales (5 detection days); right whale detections initiated a slow zone |
| Early fall (September) 2024 gap-fill |  |  |
| ru43 | No Rx-Live data. Awaiting VMT data from MATOS data push (in progress). | N/A. No DMON sensor. |
| Fall 2024 paired |  |  |
| ru39 | No Rx-Live data. Awaiting VMT data from MATOS data push (in progress). | N/A. No DMON sensor. |
| ru40 | 236 detections from 25 tags (preliminary from Rx-Live), official results and contact points waiting for MATOS data push (in progress). | 26 total whale detection days, including sei whales (1 detection day), fin whales (21 detection days), and humpback whales (26 detection days) |

Marine mammal detections observed during the Fall 2024 glider mission.

Active acoustic data: Active acoustic data from the glider AZFP sensors have been initially processed and analyzed for the Summer/Fall gap-fill and Fall 2024 paired missions, but we are still in the process of quality control and refining the analyses. Specifically, we are gathering NJDEP trawl data to identify potential common pelagic fish scatterers, which will allow for estimates of concentration and biomass; for now, all data regarding fish backscattering is presence/absence only.

Summer/Fall 2024 zooplankton distribution was patchy, with high concentrations of small and large copepods along basin edges between 30-75 m in depth. Total estimated copepod biomass fell between estimated biomass in Spring 2023 and 2024 at 114 g DW, with large copepods comprising 89% of that total. Small copepods comprised 85% of the total copepod concentration measured across the entire glider deployment. Median large copepod concentration was 521 individuals m-3 and median small copepod concentration was 182 individuals m-3.

A scattering pattern was observed in the Fall 2024 scattering data which had not appeared in previous deployments, consisting of a diffuse cloud that appeared in the water column around nightfall and disappeared around sunrise throughout the deployment. The behavior of this scattering cloud is consistent with several species that undergo diel vertical migration; analysis is still being carried out to determine the specific organisms that made these echoes, but possible species include mysids (shrimp) and larval squid. Beyond that, we observed echoes consistent with gelatinous zooplankton and fish both with and without swim bladders. Most of these echoes were concentrated towards the seafloor, but some were located in the middle of the water column.

Estimated zooplankton abundance from the Summer/Fall 2024 gapfill mission, and presence/absence data of pelagic fishes from Fall 2024 paired mission. Top left panel: Depth-integrated total zooplankton biomass (individuals/m2) measured along glider transects; no marine mammal detection data are available for this mission as it was not paired with a DMON. Wind lease areas highlighted in salmon color. Top right panel: Zooplankton (log10; individuals/m3) estimated from the Summer/Fall 2024 mission over deployment time and depth (in meters). The figure indicates daytime (white) and nighttime (gray bars) as well as locations where sampling was conducted inside (pink bars) or outside (white) wind farm lease areas. The seafloor is indicated by the solid black line (note: these depth data are interpolated/smoothed, and thus some biomass data points may appear below the seafloor). For the zooplankton mission, the concentration data include only that from copepods, and the dominant zooplankton (scatterers) identified in the replicate zooplankton net tows that were conducted at glider deployment and recovery included the small copepods Paracalanus parvus, Oithona similis, and Centropages typicus and large copepod Calanus finmarchicus. Bottom panels: Fall 2024 presence/absence data of gelatinous zooplankton and generic swimbladder-bearing/swimbladderless fish species. The left panel shows data from the scattering cloud discussed above; the right panel has these data hidden to more clearly show the pattern of detected fish echoes.

Difficulties Encountered:

ru39 was recovered from the Fall 2024 paired mission with a missing port wing and broken wing rail.

Presentations & Publications (includes only this reporting period):

Mossman, D., Kohut, J.T., Saba, G.K. 2024. Examining the Seasonal Relationships Between Oceanographic Variables and Echosounder-Derived Zooplankton Abundance Estimates Using an Autonomous Underwater Glider. Poster presented at the Mid-Atlantic Chapter of the American Fisheries Society Annual Meeting. October 2024. New Brunswick, NJ.

Nazzaro, L., Kohut, J., Saba, G., Mossman, D., Baumgartner, M., & Wilder, J. Physics, plankton, and whales, oh my! 2024 North Atlantic Right Whale Consortium Annual Meeting. October 2024. Providence, RI.

Saba, G. 2024. ‘Eco-gliders’ as novel platforms for ocean health and ecosystem monitoring and research. Invited talk presented at the Mid-Atlantic Ocean Conservation Symposium. October 2024. Monmouth, NJ.

Drinkwater, K.F., Petrie, B., Smith, P.C. 2002. Hydrographic variability on the Scotian Shelf during the 1990s. Northwest Atlantic Fisheries Organization Scientific Council Meeting, June 2002. Serial No. N4653, NAFO SCR Doc. 02/42, https://www.nafo.int/Portals/0/PDFs/sc/2002/scr02-042.pdf.

Record, N., Pershing, A., Rasher, D.B. 2024. Early warning of a cold wave in the Gulf of Maine. Oceanography, https://doi.org/10.5670/oceanog.2024.506.